## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
DEF-001 | Sejal Shinkar | 2026-08-21 | ChromaDB retrieval query fails with IndexError when question string is empty or whitespace | Sprint 1 | Sejal Shinkar | Logical | Added validation check and defaulted query_str to 'general facts' when question is blank | 2026-08-24 | Closed | Verified with test_rag_retrieval_fallback
DEF-002 | Sejal Shinkar | 2026-08-25 | SQLite database lock error (sqlite3.OperationalError: database is locked) under rapid sequential insertions | Sprint 1 | Sejal Shinkar | Maintainability | Enabled SQLite WAL journal mode and added timeout=15 in connection context manager in storage.py | 2026-08-26 | Closed | Concurrency stress test passed with zero database lock contention
DEF-003 | Sejal Shinkar | 2026-09-02 | Google Gemini API raises 429 ResourceExhausted (rate limit exceeded) during multi-agent concurrent evaluation | Sprint 2 | Sejal Shinkar | Others | Engineered exponential backoff auto-retry loop parsing 'retry in Xs' header with asyncio.sleep | 2026-09-03 | Closed | Implemented in BaseEvaluationAgent._invoke_gemini
DEF-004 | Sejal Shinkar | 2026-09-04 | HallucinationAgent hallucination_score exceeds 1.0 boundary on malformed JSON response | Sprint 2 | Sejal Shinkar | Logical | Enforced strict score clamping: max(0.0, min(1.0, score)) and normalized groundedness complement | 2026-09-07 | Closed | Bounds validation verified in schemas.py and hallucination_agent.py
DEF-005 | Sejal Shinkar | 2026-09-09 | Gemini API model deprecation or daily free-tier quota exhaustion crashes pipeline with 500 server error | Sprint 2 | Sejal Shinkar | Others | Built intelligent offline deterministic fallback engine (_mock_fallback) ensuring seamless zero-downtime evaluation | 2026-09-10 | Closed | Fault tolerance validated; offline mode triggers automatically on quota limits
DEF-006 | Sejal Shinkar | 2026-09-16 | CSV batch ingestion fails to parse Windows CSV files with UTF-8 BOM encoding and semicolon delimiters | Sprint 3 | Sejal Shinkar | Standards | Integrated csv.Sniffer for automatic delimiter detection (comma/tab/semicolon) and stripped UTF-8 BOM | 2026-09-17 | Closed | BatchEvaluator now handles diverse enterprise CSV exports cleanly
DEF-007 | Sejal Shinkar | 2026-09-18 | Fluent contradictory AI response passed with weighted score 0.638 due to high relevance and completeness | Sprint 3 | Sejal Shinkar | Logical | Engineered deterministic Critical Failure Overrides forcing immediate 'Fail' verdict on factual contradictions | 2026-09-21 | Closed | Safety guardrail verified; contradictory response correctly fails
DEF-008 | Sejal Shinkar | 2026-09-22 | User customized dimensional weights deviating from 1.0 causing unnormalized composite scoring | Sprint 3 | Sejal Shinkar | Logical | Implemented automatic weight normalization: w_i = w_i / sum(w_j) whenever ¦sum - 1.0¦ > 1e-4 | 2026-09-23 | Closed | VerdictAgent guarantees strict sum(w) == 1.0 constraint
DEF-009 | Sejal Shinkar | 2026-09-30 | Dashboard metrics table overflows horizontally on small smartphone viewports (< 480px width) | Sprint 4 | Sejal Shinkar | User Interface | Added CSS responsive media queries, flex-wrap layout tokens, and table horizontal scroll containers | 2026-10-01 | Closed | Verified responsive rendering on Chrome mobile emulation and iOS Safari
DEF-010 | Sejal Shinkar | 2026-10-02 | ReportLab PDF report generation truncates long multi-line prompt texts exceeding single page boundaries | Sprint 4 | Sejal Shinkar | User Interface | Wrapped table cells with autowrapping Paragraph flowables and dynamic ColumnWidth calculations | 2026-10-05 | Closed | Multi-page PDF export renders cleanly across 100+ batch records
DEF-011 | Sejal Shinkar | 2026-10-06 | Markdown documentation displays red KaTeX error boxes ('_ allowed only in math mode') in previewers | Sprint 4 | Sejal Shinkar | Standards | Replaced pseudo-math \text{..._...} blocks with clean code blocks and formal mathematical subscripts | 2026-10-07 | Closed | All 10 documentation markdown files render with 0 KaTeX errors
DEF-012 | Sejal Shinkar | 2026-10-07 | Docker container startup crash loop with 'ImportError: pyarrow requires NumPy 2.0 or newer, found 1.26.4' | Sprint 4 | Sejal Shinkar | Maintainability | Pinned pyarrow>=14.0.0,<18.0.0 and numpy>=1.24.0,<2.0.0 in requirements.txt to ensure ABI compatibility | 2026-10-08 | Closed | Container build and startup passes health checks cleanly
DEF-013 | Sejal Shinkar | 2026-10-08 | Render cloud container killed with 'Memory limit exceeded (> 512 MB)' during RAG embedding execution | Sprint 4 | Sejal Shinkar | Others | Engineered ultra-low-memory deterministic subword feature embedding engine (< 0.1 MB RAM), eliminating PyTorch | 2026-10-09 | Closed | Container memory dropped from 944 MB to 140 MB; deployed and live on Render

## Sheet2
Logical
User Interface
Maintainability
Standards
Others